## Sheet1
ID | Feature | Test | Expected Result | Actual Result | Action
1 | Goal_Search | Agent Enters and Processes Goal | Agent should pick random locations in the world and travel to them. Upon reaching them, it should then move to another etc. | Failed as it keeps picking the same position occassionally and will often get stuck in the same spot | Added simple recursive test to ensure currently selected position isn't the same as the one we're at. FIXED
1.1 Retest |  | Agent Enters and Processes Goal | Agent should pick random locations in the world and travel to them. Upon reaching them, it should then move to another etc. | Agent picks random locations in the world and travels to them. Upon reaching them, it then movem to another etc.
2 | Goal_AttackEnemy | Agent Enters and Processes Goal | Agent should have a target and begin closing the distance between them and attacking when it's range. | Fails as the AI will sometimes just get stuck and stop where it is. | Agent loses track of target and then never actually re-assigns it so it get's stuck in goal. Fixed by making agent now re-assign target.
2.1 Retest |  | Agent Enters and Processes Goal | Agent should have a target and begin closing the distance between them and attacking when it's range. | Agent get's a target and begins closing the distance between them and attacking when it's range.
3 | Goal_CollectFlag | Agent Enters and Processes Goal | Agent should move toward and collect the flag when in range of it and return complete when it has collected it. | Agent get's near flag but never does anything when in vicinity of it. | Seems that the collectable list in senses doesn't filter with the flag so the problem is fixed with a new approach in which we fix the basic sensing system by including flags in a collectable search.
3.1 Retest |  | Agent Enters and Processes Goal | Agent should move toward and collect the flag when in range of it and return complete when it has collected it. | Works as intended and flag is collected upon reaching it and complete is returned.
4 | Goal_DropObject | Agent Enters and Processes Goal | Agent should drop given item from their inventory when in range and return complete when it's done this. | Agent drops item from their inventory if they have it and returns complete when it's done this.
5 | Goal_FindFlag | Agent Enters and Processes Goal | Agent should attempt to move toward either the enemy team's base or the last known flag position and then complete when it has reached there. | Agent successfully navigates towards the positions and returns complete upon arrival.
6 | Goal_GetItem | Agent Enters and Processes Goal | Agent should attempt to collect item when in range of it and if not it should move closer. Upon collection it should return complete. | Agent fails to collect item as it doesn't seem to see it. | Seems that I used the wrong sight list by accident. Fixed by using correct sight list.
6.1 Retest | Goal_GetItem | Agent Enters and Processes Goal | Agent should attempt to collect item when in range of it and if not it should move closer. Upon collection it should return complete. | Agent fails as it steals item from each other's inventory without the system ever updating this change. | Seems the bot sensing has an inherent bug in which it never actually checks to see if it can physically see the object before attempted to grab it. Fixed by adding in visual check to provided sensing system.
6.2 Retest | Goal_GetItem | Agent Enters and Processes Goal | Agent should attempt to collect item when in range of it and if not it should move closer. Upon collection it should return complete. | Agent successfully navigates towards item and collects it.
7 | Goal_UseItem | Agent Enters and Processes Goal | Agent should attempt to use item if it has it in it's inventory. Returns complete if it has it. | Agent attempts to use item if it has it in it's inventory. Returns complete if it has it.
8 | Goal_MoveToBase | Agent Enters and Processes Goal | Agent should move toward friendly base and return complete when it has reached there. | Agent moves toward friendly base and returns complete when it's reached it.
9 | Goal_Heal | Agent Enters and Processes Sub Goals and Exits When Finished | Agent should process sub goals by first heading toward health kit spawn location and then grabbing it if it's there. | Agent fails as it stays in moving toward health kit goal | Seems there was a flaw in the sub goal processing of the composite goal abstract class. Fixed by allowing it to remove goals from the stack when they're complete.
9.1 Retest | Goal_Heal | Agent Enters and Processes Sub Goals and Exits When Finished | Agent should process sub goals by first heading toward health kit spawn location and then grabbing it if it's there. | Agent processes sub goals and heads toward health kit and collects it if it's there. Succesfully returns complete and failed when it's collected and when it's not there.
10 | Goal_GetFlag | Agent Enters and Processes Sub Goals and Exits When Finished | Agent should process sub goals by first heading toward las known location of flag and then grabbing it if it's there. | Agent succesfully finds and grabs the flag when it's there and returns the correct states.
11 | Goal_ScoreFlag | Agent Enters and Processes Sub Goals and Exits When Finished | Agent should process sub goals by first returning to home base and then dropping the flag when in range. | Agent fails as it heads toward the wrong base. | Seems that I had the wrong base set for move to base when passing it from the evaluator. Fixed by using it's own internal tracker of friendly base in the AgentData class
11.1 Retest | Goal_ScoreFlag | Agent Enters and Processes Sub Goals and Exits When Finished | Agent should process sub goals by first returning to home base and then dropping the flag when in range. | Agent succeeds and drops flag when in base.
12 | Evaluator_AttackEnemy | Fed a fixed set of values | Returns 0.354 with input data | Returns 0.354
13 | Evaluator_GetPowerup | Fed a fixed set of values | Returns 0.629 with input data | Return 0.629
14 | Evaluator_UsePowerup | Fed a fixed set of values | Returns 0.19 with input data | Return 0.19
15 | Evaluator_Search | Fed a fixed set of values | Returns 0.52 with input data | Returns 0.52
16 | Evaluator_GetEnemyFlag | Fed a fixed set of values | Returns 0.37 with input data | Returns incorrect result | Equation was done wrong. Fixed by wrapping 1-d inside of parenthesis to ensure it happens before the multiplication
16.1 Retest | Evaluator_GetEnemyFlag | Fed a fixed set of values | Returns 0.37 with input data | Returns 0.37
17 | Evaluator_RetrieveLostFlag | Fed a fixed set of values | Returns 0.75 with input data | Returns 0.75
18 | Evaluator_ScoreEnemyFlag | Fed a fixed set of values | Returns 0.2 with input data | Returns 0.2
19 | Evaluator_ScoreFriendlyFlag | Fed a fixed set of values | Returns 0.2 with input data | Returns 0.2
20 | Evaluator_Heal | Fed a fixed set of values | Returns 0.681 with input data | Returns incorrect result | Equation was done wrong. Fixed by wrapping 1-h inside of parenthesis.
20.1 Retest | Evaluator_Heal | Fed a fixed set of values | Returns 0.681 with input data | Returns 0.681
21 | Health | Fed a fixed set of values | Returns 0.5 with input data | Returns 0.5
22 | DistanceToPosition | Fed a fixed set of values | Returns 0.16 with input data | Returns 0.16
23 | DistanceToObject | Fed a fixed set of values | Returns 0.16 with input data | Returns 0.16
24 | Strength | Fed a fixed set of values | Returns 1 with input data | Returns 1
25 | NumberOfEnemiesInSight | Fed a fixed set of values | Returns 0.33 with input data | Returns 0.33
26 | Goal_Globals | Evaluators selected correctly | Agent should loop through all available evaluators and select the one with the highest desirability | Agent successfully manages to select correct evaluator with highest desirability
27 | Goal_Globals | Goals changed correctly | Agent should change current goal to desired goal correctly | Fails as agent keeps changing it's desired goal too frequently never giving it a chance to actually perform the one it's in. | Fixed: By simply adding a check to determine if the desired goal is the one we are already in, if it is, there's no point switching it.
27.1 Retest | Goal_Globals | Goals changed correctly | Agent should change current goal to desired goal correctly | Agents change current goal to desired goal correctly and don't bother if w'ere already in it.
26 | Combined Test | Agents function with evaluators controlling goals | Agents should function indepently with evaluators selecting goals based on desirability. Different goals should be selected based on what's happening around them. | Failed as AI lose track of agent data and results in null reference exception error from several goals. | Fixed: Removed teammates from collection when they've died and re-add them upon re-spawning.
26.1 Retest | Combined Test | Agents function with evaluators controlling goals | Agents should function indepently with evaluators selecting goals based on desirability. Different goals should be selected based on what's happening around them. | Agents successfully function with evaluators picking goals as they play. Values need tweaking as expected.